## Slide 1
Planning and Estimation

## Slide 2
You have a bunch of user stories, so what’s next?

## Slide 3: Iterative Development Process
Requirements
Planning
Analysis
Design
Implementation
Deployment
Testing
Evaluation
Initial Planning
We are here

## Slide 4
Choose USs for Iteration
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers
Get to Work!
Developer
Customer
Create USs
Requirements
USs
Check USs
Corrections/Clarifications
Fix USs
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities

## Slide 5
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 6: Estimating Time
http://xkcd.com/1658/

## Slide 7: Hofstadter's Law
It always takes longer than you expect, even when you take into account Hofstadter's Law.
— Douglas Hofstadter, Gödel, Escher, Bach

## Slide 8: Mythical Man Month
“Adding manpower to a late project makes it later.”
  Group communication grows very fast
  n(n – 1) / 2

## Slide 9: Mythical Man Month
“Adding manpower to a late project makes it later.”
  Group communication grows very fast
  n(n – 1) / 2
“How does a large project get to be one year late?”
“One day at a time.”
  Lot of small milestones miss deadlines by a bit

## Slide 10: Principles for Estimation
Principle: Past performance is the best indicator of future performance
  Approach: Track your outcomes; refine your estimates
Principle: Wisdom of the crowd
  Goal: Predict how events will unfold
    Think event planning
  Problem: Easy to miss something
  Solution: More brains = more opportunities to catch eventualities

## Slide 11: Principles for Estimation
Principle: Past performance is the best indicator of future performance
  Approach: Track your outcomes; refine your estimates
Principle: Wisdom of the crowd
  Goal: Predict how events will unfold
    Think event planning
  Problem: Easy to miss something
  Solution: More brains = more opportunities to catch eventualities
How did the first
Iteration go??

## Slide 12: Planning Poker!

## Slide 13: Estimation with Planning Poker
Cards with units of work: 0,1/2,1, 3, 5, 8, 13, 21, 34…
  Assume team can do X units in an iteration
  Units can be hours or days
For each US:
  Discuss work involved
  Flip cards
  Repeat until consensus
Efficiency in estimating is important
  Don’t expect your estimates to be super accurate

## Slide 14
Let’s watch this video to find out what planning poker is all about:
http://youtu.be/0FbnCWWg_NY

## Slide 15: More Estimation Principles
Engineers refine estimates; customers refine expectations
  Estimates are basis for customer’s cost assessment
Give honest estimates that customers can trust
  Don’t do this: https://youtu.be/t9SVhg6ZENw
Work at a sustainable pace
  No heroes, no all-nighters, no super-human feats
  Either you get the code done like a human being, or you don’t

## Slide 16
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 17: Principle: Customer sets priorities
Ensures alignment with customer goals
Helps customer feel in control
  Project isn’t going “off the rails”
Estimates help customer maximize cost-benefit

## Slide 18: Priority Numbering Scheme
P0 – drop everything, critical task, often fatal bugs
P1 – high priority, others depend on this
P2 – should be completed during iteration
P3 – only complete if time permits
P4 – low value or superficial, don’t spend time on it

## Slide 19: So now you have…
Collection of user stories
  With estimates
  And customer priorities
What’s next?

## Slide 20: Let’s try it out
Go to your GitHub issues
If they are lacking details, add to the description
Add a comment:
  Estimate the hours it will take you
  Add a priority level

## Slide 21
Create USs
Requirements
USs
Corrections/Clarifications
Add Estimates
USs + Estimates
Add Priorities
USs + Estimates + Priorities
Check USs
Choose USs for Iteration
Get to Work!
Developer
Customer
Fix USs
Divide Chosen USs into Tasks
Estimate Tasks
Assign Tasks to Workers

## Slide 22: From USs to Tasks
Estimate
User Story

## Slide 23: Incremental Development Principle
Each task produces running code
  Unit tests count

## Slide 24: Task design strategy
Make tasks build upon one another
  First task makes subset of US work (e.g., partial form)
  Second task makes bit more work (e.g., add persistence)
  Etc…

## Slide 25: Planning Process
Part 1: Estimate USs
  Use Planning Poker
  Start designing
Part 2: Collect customer priorities
  Assign number each US
  Also note any corrections/clarifications
Part 3:
  Choose tasks for the iteration
    2 weeks worth of work
  Fill out iteration plan with what each team member will do
    Everyone codes
    Tasks must be verifiable and executable